## Byte&Bit - GanttChart.ai
[6 empty] | August 2025 | [15 empty] | September 2025 | [29 empty] | October 2025 | [30 empty] | November 2025 | [29 empty] | December 2025 | [30 empty] | January 2026 | [30 empty] | February 2026
Workstream | Task | Team | Duration | Start Date | End Date | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Planning
| Define project scope and objectives. | Byte&Bit | 3 | 2025-08-18 | 2025-08-20
| Identify stakeholders and establish a communication plan. | Byte&Bit | 2 | 2025-08-21 | 2025-08-22
| Develop project schedule and assign roles. | Byte&Bit | 4 | 2025-08-25 | 2025-08-28
Development
| Conduct initial team onboarding and training. | Byte&Bit | 3 | 2025-08-29 | 2025-09-02
| Implement and integrate Dynamic Pricing and Delivery Optimization solutions. | Byte&Bit | 8 | 2025-09-18 | 2025-09-29
| Initiate location expansion and workforce optimization activities. | Byte&Bit | 5 | 2025-09-30 | 2025-10-06
| Develop and implement solutions for sentiment analysis and energy optimization. | Byte&Bit | 6 | 2025-10-14 | 2025-10-21
Requirement Analysis
| Establish data requirements for i1 and i2 workstreams. | Byte&Bit | 5 | 2025-09-03 | 2025-09-09
Design
| Create and finalize design documentation for Dynamic Pricing and Delivery Optimization. | Byte&Bit | 6 | 2025-09-10 | 2025-09-17
Testing
| Conduct testing for Dynamic Pricing and Delivery Optimization features. | Byte&Bit | 4 | 2025-09-30 | 2025-10-03
Review
| Review and approve Dynamic Pricing and Delivery Optimization results with stakeholders. | Byte&Bit | 3 | 2025-10-06 | 2025-10-08
| Conduct final reviews for i4 deliverables and prepare for i5 transition. | Byte&Bit | 3 | 2025-10-28 | 2025-10-30
Analysis
| Analyze inventory waste and upselling opportunities during i1 and i2 execution. | Byte&Bit | 5 | 2025-10-07 | 2025-10-13
Coordination
| Prepare for i3 tasks and ensure inter-team coordination. | Byte&Bit | 4 | 2025-10-22 | 2025-10-27
Documentation
| Document project learnings and outcomes for future reference. | Byte&Bit | 2 | 2025-10-31 | 2025-11-03